## Sheet1
ADVANCED QUALITY PLANNING CHECKLIST NEW / EXISTING JOBS
NEW PARTS / JOBS
| ATTENDEES: |  | Dave Hunt, Mark Brockman |  |  |  | PART NUMBER: _________________________________ |  |  | 71097-0C040, 0C030, 0C050
Kyle Lussier, Lisa Bilbrey, Tom Brockman
| Mike Pare, Lionel Peltier, Greg Peltier | [5 empty] | PPAP DATE / LEVEL : ____________________________ |  |  | PPAP Date less R@R 3-19-07
Phil Fairley, Rob Purves, Ryan Lowrie
[7 empty] | PRODUCTION START DATE: ______________________ |  |  |  | 2007-11-30
| DATE: | 2-09-07 Revision
[7 empty] | VOLUME: ______________________________________ |  | Total all 3 parts are 100,000 parts per year
| CUSTOMER: _______________________________ |  | Trim Masters |  |  |  | EXISTING PARTS / JOBS
| PLANT (S) RESPONSIBLE:___________________ |  |  | PPI |  |  | CURRENT LOCATION(S): ________________________
| SALES REP:_______________________________ |  | Dave Hunt |  |  |  | NEW LOCATION(S): _____________________________
# | PART PRINT / MATH DATA |  |  |  | YES | NO | N/A | COMMENTS |  |  |  | DATE | RESP.
1 | Ellis Tool has received math data from customer |  |  |  | X | [6 empty] | 2006-11-02 | Mark B.
2 | Prints have been generated |  |  |  | X | [6 empty] | 2006-11-02 | Mark B.
3 | Prints have been controlled and distributed |  |  |  | X | [6 empty] | 2006-02-09 | Mark B. & Ana C
4 | Manufacturing tolerances are feasible |  |  |  |  | X |  | ECR's have been submitted, we are waiting from approval from Japan. Submitted to Seth Furgeson, Steven Riggs of TMI |  |  |  | 2006-11-02 | Trim Masters Enginnering
5 | SC/CC requirements are applicable |  |  |  |  | X | [5 empty] | 2006-11-02
6 | Engineering specifications are defined |  |  |  |  | X |  | Waiting on Specs. For off shelf components. North Americian Suppliers do not recongize the specs. Listed on the cross ref. sheet provided by Trim Masters. We have requested and are waiting for support from TRIM Masters Purchasing department on this issues. |  |  |  | 2006-11-02 | Trim Masters Enginnering
i.e. material, weld, coating, torque etc.
8 | Part/component designs are final |  |  |  |  | X |  | ECR's have been submitted, we are waiting from approval from Japan |  |  |  | 2006-11-02 | Trim Masters Enginnering
9 | Supplementary drawings are required |  |  |  | X | [6 empty] | 2006-02-09 | Mark B. & Ana C
10 | Supplementary drawings are controlled and distributed |  |  |  | X | [6 empty] | 2006-02-09 | Mark B. & Ana C
1 of 3
# | FIXTURES / GAUGING |  |  |  | YES | NO | N/A | COMMENTS |  |  |  | DATE | RESP.
11 | Fixture(s) Design is complete |  |  |  | X | [6 empty] | 2007-11-06 | Kyle lussier
12 | Multiple Fixtures are required |  |  |  | X |  |  | Stamping fixtures are at Marwood and WM&S |  |  |  | 2006-12-14 | Kyle lussier
13 | Customer fixture(s) are required |  |  |  |  | X
14 | All fixture(s) designs have been reviewed/approved |  |  |  |  | X |  | ECR's submitted for datum scheme, waiting approval |  |  |  | 2006-12-14 | Kyle lussier
15 | Customer has reviewed/approved fixture designs |  |  |  |  | X |  | We have submitted request for gage approval 12-20-06. No response yet |  |  |  | 2006-12-20 | Trim Masters Enginnering
16 | Fixture builds are complete |  |  |  | X | [6 empty] | 2007-01-03 | Mike Pare
17 | Fixture(s) are certified / R&R complete |  |  |  | X | [6 empty] | 2007-01-03 | Ryan / Rob Purves
# | PPAP REQUIREMENTS |  |  |  | YES | NO | N/A | COMMENTS |  |  |  | DATE | RESP.
18 | Level 3 PPAP is required |  |  |  | X |  |  | PPAP & Tooling for level 383WAF0128 (WPC0164), We are waiting for approval on quote for change level 383WAF0150 (383WP0580, 0406, 0027, 0018)
19 | Customer has specific PPAP requirements |  |  |  | X |  |  | Per the SQAM |  |  |  | 2007-03-17 | Ryan L
20 | Customer has provided supplier manual |  |  |  | X |  |  | SQAM |  |  |  | 2006-10-20 | TMI
21 | Part dimensionals are required How many? |  |  |  | X |  |  | Per the SQAM |  |  |  | 2007-03-17 | Ryan L
22 | PPAP has been assigned |  |  |  | X |  |  | PPI Ryan Lowrie |  |  |  | 2006-12-14
23 | Other PPAP open issues |  |  |  | X |  |  | Waiting for ECR approvals and Trim Masters to help us find fasteners suppliers.
# | TOOLING |  |  |  | YES | NO | N/A | COMMENTS |  |  |  | DATE | RESP.
24 | Tool designs are complete |  |  |  | X | [6 empty] | 2006-11-02 | Mark B
25 | Manufacturing plant has reviewed designs |  |  |  | X | [6 empty] | 2006-11-02 | Mark B
26 | Additional equipment is required |  |  |  |  | X | [5 empty] | 2006-11-02 | Mark B
27 | Outsourced tooling / equipment is required |  |  |  |  | X | [5 empty] | 2006-11-02 | Mark B
28 | Tooling is complete |  |  |  | X |  |  | 1st set of tools are complete. Waiting approval for quotes sent on change requests to proceed with capacity tools |  |  |  | 2006-11-02 | Mark B
29 | Tooling has been developed |  |  |  | X | [6 empty] | 2006-12-14 | Mark B. Kyle Lussier, Ryan L
30 | Manufacturing plant has reviewed and approved tooling |  |  |  | X | [6 empty] | 2006-12-14 | Mark B. Kyle Lussier, Ryan L
2 of 3
# | SUB-COMPONENT REQUIREMENTS |  |  |  | YES | NO | N/A | COMMENTS |  |  |  | DATE | RESP.
31 | Outsourced components are required |  |  |  | X | [6 empty] | 2006-12-14 | Steve M, Mark B.
32 | Supplier (s) have been reviewed |  |  |  | X |  |  | Yes, through Purchasing & Engineering |  |  |  | 2006-12-14 | Steve M, Mark B.
33 | Purchase orders have been issued |  |  |  | X | [6 empty] | 2006-12-14 | SteveM
34 | Supplier evaluation/development is complete |  |  |  | X |  |  | Low risk, current suppliers no concerns |  |  |  | 2006-12-14 | SteveM, Phil F.
35 | Supplier(s) have submitted PPAP and samples |  |  |  | X | [6 empty] | 2006-12-14 | Ana C
# | EXISTING JOBS/PARTS MOVING |  |  |  | YES | NO | N/A | COMMENTS |  |  |  | DATE | RESP.
36 | Review Criteria as Referenced in FOQA081 | [5 empty] | X
37 | Review Customer Specific Issues and Requirements | [5 empty] | X
38 | Notify Customer Purchasing / Receiving Plants | [5 empty] | X
39 | Prepare PPAP/PSO for Job Transfer | [5 empty] | X
OTHER OPEN ISSUES OR CONCERNS
Part numbers for 2nd row Headrest mechanisms for the Toyota Sequoia Program. Build to print parts.
71097-0C040 40% & 60% Manual H/R Asm
71097-0C030 60% PWR H/R Asm
71097-0C050 40% PWR H/R Asm
Run at Rate Aug. 06, 2007
Internal Mts:
10-2-06, 10-9-06, 10-15-06, 10-20-06, 10-25-06, 10-27-06, 11-1-06, 11-2-06, 11-3-06, 11-4-06, 12-18-06, 1-8-06, 1-16-06
3 of 3