## Staffing Plan
Staffing/Training Plan
Support Commitment from Union (UAW Local 2381)
All management employees will be trained on all the Assembly process (s) from the prototype and development engineers. Management once trained will become the trainers.
Management will select a group of senior operators to perform the build (s). These operators will be the team leaders and will be responsible to train any new operators with managements supervision.
Management will hire and train through the training process any new staff as required.
All employee’s including management must complete the standardized Operator Training Matrix.
GMT 900 - Will require 8 employees per shift - staffing will start the end of October and staffed to capacity by the first part of Janurary in order for all employee's to be trained and ready before system fill.

## Staffing Launch Timing
GMT 900 Staffing Plan
Program Manager - Lisa Bilbrey | [25 empty] | Windsor Machine Build
Sales Manager - Scott Barko | [25 empty] | Lear Build Date
Engineer - Evan Kayaharn
Plant Manager - Lisa LeGras
Quality Manager - Marilyn Clark
Maintenance Manager - Jake Brygier
Shipping Receiving Manager - Monica Howe
| BUILD NAME | STYLE | QTY | WHO BUILDS | DUE DATE (or w/o) | [20 empty] | 2006
[6 empty] | August |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOV |  |  |  | DECEMBER |  |  |  | JANUARY
# | [5 empty] | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30
1 | TRAIN (25%) | Mixed | 50 SETS | WM&S | 2005-08-12 | bar: August 15
|  |  |  | Lear Req'd | 2005-08-27 | bar: August 22
2 | MNS3 |  |  | WM&S | 2005-08-08
|  | 922 | 12 | Lear Req'd | 2005-08-22 | bar: August 22
3 | MNS4 |  |  | WM&S | 2005-08-22 | bar: August 22
|  |  |  | Lear Req'd | 2005-09-12 | bar: SEPTEMBER 12
4 | MS1 |  |  | WM&S | 2005-08-22 | bar: August 22
|  | 922 | 36 | Lear Req'd | 2005-09-12 | bar: SEPTEMBER 12
5 | TRAIN (75%) | Mixed | 180 SETS | WM&S | 2005-09-19 | bar: SEPTEMBER 19
|  |  |  | Lear Req'd | 2005-10-08 | bar: OCTOBER 3
6 | MS2 |  |  | WM&S | 2005-09-19
|  | 922 | 47 | Lear Req'd | 2005-09-28
7 | MS2A |  |  | WM&S | 2005-09-19
|  | 922 | 23 | Lear Req'd | 2005-09-28
8 | TRAIN (100%) | Mixed | 240 SETS | WM&S | 2005-10-10
|  |  |  | Lear Req'd | 2005-10-29
9 | MS3 |  |  | WM&S | 2005-10-10
|  | 922 | 30 | Lear Req'd | 2005-10-24
10 | MS4 |  |  | WM&S | 2005-10-24
|  | 922 | 65 | Lear Req'd | 2005-11-07
11 | MNS5 |  |  | WM&S | 2005-11-28
|  |  |  | Lear Req'd | 2005-12-12
12 | MS5 |  |  | WM&S | 2005-11-28
|  | 922 | 22 | Lear Req'd | 2005-12-12
13 | STARTUP 922 at GM |  |  |  | 2006-01-09
Management training
Hire nine employee's
Internal Time Study
Hire nine employee's

## Suppier Readiness
Sub-Supplier Readiness
Det# | Part Number | Sub Component | HST# | Supplier | TAX ID / GST # | Price | FUNDS | Country of origin | qty | Ctns.
1 | Duon Washer | Rattle Washer | 7318.22.9000 | MIT |  | 0.005 | US | US | 300 | 1
14 | No. 006 | O-ring | 7318.22.9000 | ? Mc Masters | 382439612 | 0.08 | US | US | 400 | 1
6 | L0057918AA-01 | Screws | 7318.15.9039 | ? purchased item Fastenal | 410948415 | 0.0464 | US | US | 600 | 1
13 | L0098393AA-02-LCF | Bezel | 9401.90.9090 | Brahm | 138131867 | 0.093 | CA | CA | 364 | 2
12 | L0098391AA-01-LCF | Button | 9401.90.9090 | Brahm | 138131867 | 0.0803 | CA | CA | 364 | 2
5 | L0057915AA-02 | Front Cover | 9401.90.9090 | Brahm | 138131867 | 0.3026 | CA | CA | 364 | 8 | @ 70
3 | L0057913AA-03 | Plastic Shell | 9401.90.9090 | Brahm | 138131867 | 1.2718 | CA | CA | 364 | 10 | @ 30
4 | L0057914AA-02 | Actuator Arm | 9401.90.9090 | ELLIS |  | 0.25 | US | CA | 220 | 1
9 | L00783711AA | Foam | 9401.90.9090 | Centroy |  | 1 | CA | CA | 120 | 20
| L0070617AA01G13 | Trim cover | 9401.90.9090 | IRVIN | 383254095 | 12.167 | US | MEX | 3 | 1
| L0070617AA01G91 | Trim cover | 9401.90.9090 | IRVIN | 383254095 | 12.167 | US | MEX | 44 | 1
LAURA ESQUEVIEL
734-341-8122

## Supplier Time Lines
Sub-Supplier Readiness
Verify part numbers match BP
DET# | Part Number | BP | BAR CODES | ZENA | Sub Component | Supplier | Tooling | Full PPAP | Run @ Rate
17 |  |  |  |  | Welded Frame Asm | Pellus
16 | L0058601AA-04-LCF |  |  |  | Button ASM | Brahm
15 | Velcro pad |  |  |  | Velcro | ? Aplex
14 | No. 006 |  |  |  | O-ring | ? Mc Masters
13 | L0098393AA-02-LCF |  |  |  | Bezel | Brahm | 2005-07-27 | 2005-07-27
12 | L0098391AA-01-LCF |  |  |  | Button | Brahm | 2005-07-27 | 2005-07-27
11 | L0098386AA-01 |  |  |  | Rubber Bumper | Brahm | 2005-09-30 | 2005-09-30
10 | L0098382AA-01_comp |  |  |  | Button Spring | Brahm | 2005-09-30 | 2005-09-30
9 | L00783711AA |  |  |  | Foam | Centroy
8 | L0061964AA-01 |  |  |  | Extension Spring | Dominion Spring | 2005-09-12 | 2005-09-12
7 | L0057928AA-01 |  |  |  | Headrest Rod | Pellus
6 | L0057918AA-01 |  |  |  | Screws | ? purchased item fastenal
5 | L0057915AA-02 |  |  |  | Front Cover | Brahm | 2005-07-27 | 2005-07-27
4 | L0057914AA-02 |  |  |  | Actuator Arm | Canada Stampings | 2005-07-12 | 2005-07-12 | 2005-07-14 | 32 part / min. X 60 min. = 1920pcs per hr. X 8 hrs = 15,360pcs. Per shift
3 | L0057913AA-03 |  |  |  | Plastic Shell | Brahm | 2005-07-27 | 2005-07-27
2 | L0057912AA-02 |  |  |  | Graduated Lever | GFM | 2005-07-23 | 2005-08-05
1 | Duon Washer |  |  |  | Rattle Washer | ? MIT
| PART NUMBER |  |  |  | DESCRIPTION | SUPPLIER

## Inventory Sheet
GMT900 Component Inventory
2005-09-12
| Part Number | QTY @ Centroy | QTY ON ORDER PO's Issued | Sub Component | Supplier
20 | L0070617AA01G3V |  |  | Trim cover = Very Lt Cashmere | IRVIN
19 | L0070617AA01G13 |  |  | Trim cover = Ebony | IRVIN
18 | L0070617AA01G9I |  |  | Trim cover = Cashmere | IRVIN
17 | L0025993AA-05 |  |  | Welded Frame Asm | Wajax / Pellus
16 | L0058601AA-04-LCF |  |  | Button ASM | Brahm after 9-30-05
15 | Velcro pad |  |  | Velcro | ? Aplex not sourced
14 | No. 006 |  |  | O-ring | ? Mc Masters not sourced
13 | L0098393AA-02-LCF |  |  | Bezel | Brahm
12 | L0098391AA-01-LCF |  |  | Button | Brahm
11 | L0098386AA-01 |  |  | Rubber Bumper | Brahm after 9-30-05
10 | L0098382AA-01_comp |  |  | Button Spring | Brahm after 9-30-05
9 | L00783711AA |  |  | Foam | Centroy
8 | L0061964AA-01 |  |  | Extension Spring | Dominion Spring
7 | L0057928AA-01 |  |  | Headrest Rod | Pellus
6 | L0057918AA-01 |  |  | Screws | ? purchased item fastenal not sourced
5 | L0057915AA-02 |  |  | Front Cover | Brahm
4 | L0057914AA-02 |  |  | Actuator Arm | Canada Stampings
3 | L0057913AA-03 |  |  | Plastic Shell | Brahm
2 | L0057912AA-02 |  |  | Graduated Lever | GFM
1 | Duon Washer |  |  | Rattle Washer | ? MIT not sourced

## Lear GMT 900 Chart
GMT900 TIMING CHART
Roll out timing to suppliers
3/10/05
Supplier PPAP to Lear Due (non-saleable)
5/6/05
MARCH
JUNE
JULY
AUGUST
SEPTEMBER
OCTOBER
Lear PPAP to G.M. Due (non-saleable)
6/6/05
Supplier PPAP to Lear Due (Saleable)
7/5/05
Lear PPAP to G.M. Due (Saleable)
9/16/05
9/26/05
Supplier PPAP to Lear Due (Final)
NOVEMBER
Lear PPAP to G.M. Due (Final)
11/10/05
DATE CHANGED (FROM 12/15/05)
DATE CHANGED (FROM 11/15/05)
DATE DID NOT CHANGE
DATE DID NOT CHANGE
DATE DID NOT CHANGE
DATE DID NOT CHANGE
5/10/05 - 11/10/05 LAB TESTING / SOLAR TESTING
Post Grain Approval on Production Tool (6/15 - 8/15)
8/15/05
3/1/05 - 5/1/05
Resin Matl/Visual/Zenon Approval Req.
PRODUCTION TOOLING COMPLETE FOR SOLAR TEST
DATE DID NOT CHANGE
IF PRODUCTION TOOLING IS NOT COMPLETE SUPPLIER PPAP WILL BE DELAYED
APRIL
MAY
5/6/05 - 6/6/05 INTERIM AAR's

## Training Matrix
EMPLOYEE NAME | groot jeff |  |  |  |  | CENTROY ASSEMBLY EMPLOYEE TRAINING
The operation enter your initials in the corresponding box. If you have not been trained on the operation or its inspection leave the box blank.
Part Number | Operation | Initials | Part Number | Operation | Initials | Part Number | Operation | Initials | Part Number | Operation | Initials
10239899 | Spring |  | Greasers | Support |  | 88897672 | Assemble |  | FOAM LINE
| Bushings |  |  | ADV00069 (CLIP) |  |  | Screw |  | LINE OPERATOR
| Assemble | [5 empty] | Pack |  | PACKER
| Clip |  | 6L6-F | Nyliner Greaser
| Pack |  |  |  |  | L0069737AA | Assemble |  | U251 | Shaft Assembly
|  |  | Shrink Wrap Machine |  |  |  | Screw |  |  | Post Assembly
315526 AA | Clip to rod | [5 empty] | Pack |  |  | Spring
| Shell to rod |  | GMX 272 | Vacuum | [5 empty] | Side Cover
| Pack |  |  | Clip Close |  | L007787AA | Assemble |  |  | Cable
D219 |  |  |  | Pack |  |  | Screw |  |  | Shell
Front Row | Vacuum | [5 empty] | Pack |  |  | Testing
| Clip close out |  | 3RD ROW MECH | Assemble Stamping | [5 empty] | Inspect/Pack
| Pack |  |  | Rivot
Second Row | Vacuum |  |  | Asm Pawl Shaft
| Clip close out |  |  | Pawl Nut
| Pack |  |  | End of Line Tester
2nd row Center | Vacuum |  |  | Vac |  |  |  | GP-12 INSPECTION
| Clip close out |  |  | Close Out |  |  |  | Harassment Policy
| Pack |  |  | Pack |  |  |  | Employee Hand Book
2nd Row Outer | Vacuum | [6 empty] | Emergency Spill Training
| Clip close out |  | GMT 900 | Pre Assemble |  |  |  | ISO 14001 AWARENESS
| Pack |  |  | Assemble |  |  |  | QS 9000 AWARENESS
Third Row | Vacuum |  |  | Vaccum |  |  |  | PRODUCTION SHEETS
| Clip close out |  |  | Close out/ Button Instal |  |  |  | WORK ORDER CARDS
| Pack |  |  | Inspect / Pack |  |  |  | HOURLY AUDITS
| Testing | [6 empty] | TRACEABILITY
Trimming Foam | [7 empty] | FIRST OFFS
SCRAP SHEETS
ORIENTATION
WHMIS
LOCK OUT
LIFT TRUCK
DATE |  |  |  | UPDATE |  |  |  | FIRST AID
MANAGEMENT |  |  |  | MANAGEMENT
SIGNATURE |  |  |  | SIGNATURE
Controlled Copy When In Red
May not be latest revision if not in red.
CHECK WITH MASTER COPY

## Capacity Study
WINDSOR MACHINE HEADREST ASM
GMT 900 Capacity plan
2005-10-03
Based on the following
hours per shift | 7.5
shifts per day | 2
days a week | 5
Days per year standard | 240
Part Numbers | Row | Quoted Volume | 15 % increases | Parts per year | Parts per day | Parts per shift | Parts produced per hour
Combined Volume for all part numbers
L0084483AA04G9I | Front Row 4 Way | 264000 | 303600 | 303600 | 1265 | 632.5 | 84.3333
L0084483AA04G3V
L0084483AA04G13
Operations
Pre Assemble | 1 Employee per Shift
Mech Assembly | 2 Employee's per Shift
Vacuum | 2 Employee's per Shift
Close out / button Installation | 2 Employee's per Shift
Pack & Inspect | 1 Employee per Shift
GP 12 | 1 Employee per Shift
Total | 9 Employee's per Shift
18 Employee's required in total