## 3-6-06
U222 2nd / 3rd Row APQP
Meeting Minutes |  | 2006-03-06
Attendees: Phil Fairley / Lisa Bilbrey / Steve Markoc / Scott Barko / Greg Peltier / Lionel Peltier /
Dave Zultec / Paul Drouillard / Phil Bryan / Kyle Lussier / Dick St.Pierre / Tom Brockman / Todd Van Hal
Items:
1 | Windsor Machine Key Dates Established:
* | 2006-03-10 | Weld Fixtures and Weld Inspection fixtures must be complete and ready to use. The
customer will be coming to watch the welding operation.
* | 2006-03-14 | Riviting and assembly equipment must be complete and ready to use. The customer
will be coming to watch the assembly operation for the 1PP build which is 175 vehicles
* | 2006-04-03 | All capital equipment and facilities to be ready so that training of employees can start.
plan for approximately 1000pcs of internal training parts
* | 2006-04-17 | Run @ Rate scheduled. All equipment / facilities / staff / resources to be implemeted
and operational.
* | 2006-04-24 | PPAP off of production equipment and components.
* | 2006-06-15 | Full production to start or as per releases.
2 | Key Equipment Needed To Be Complete By 3/10/06:
* | 1 Weld fixture for each part will be complete and ready for development on 3/08/06
* | Weld fixtures scheduled to be ready to run at Southern Wire on the robot for 3/10/06
* | 2nd Row Weld checking fixture complete but needs to be laid out.
* | 3rd Row Weld checking fixture design complete and is being built. Scheduled to be complete
by 3/9/06
* | 2nd and 3rd row pitch checking fixtures scheduled to be complete on 3/8/06
3 | Key Equipment Needed to Be Complete By 3/14/06
* | 2nd row shell assembly fixture scheduled to be complete by 3/8/06
* | 3rd row shell assembly fixture design is complete. Scheduled to be built and complete by 3/13/06
* | 3rd row riviting machine scheduled to be @ PMS late on 3/08/06. PMS to complete rivitor and have
operational by 3/14/06
* | 1 3rd row assembly table scheduled to be complete and @ Wajax for 3/8/06
4 | Phil Bryan to bring down 1 screw gun and 1 arm to use for 3rd row build. Scheduled to be at
Wajax for 3/09/06
5 | George H. to assist in welding of frames at Southern Wire during build.
6 | Lisa Legras to build at least 1 day worth of inventory on the U251 60/40 mech. So that U222 2nd
row build can take place at Centroy on 3/14/06 without effecting production.
7 | Scott to provide the team with the permits from JCI to use mechanical plating on both 2nd and
3rd row post.
8 | Scott to make JCI aware that we will not be using the production intent screw for this build and
to obtain a permit.
U222 2nd / 3rd Row APQP
Meeting Minutes |  | 2006-03-06
Attendees: Phil Fairley / Lisa Bilbrey / Steve Markoc / Scott Barko / Greg Peltier / Lionel Peltier /
Dave Zultec / Paul Drouillard / Phil Bryan / Kyle Lussier / Dick St.Pierre / Tom Brockman / Todd Van Hal
9 | Components:
Status of all required components reviewed. The following components identified as potential risks.
* | 1350479_PIA07 Nylon coated cable for release cable assembly. Confirmation received from Capro
cable is being shipped on 3/7/06 scheduled for next day delivery to Ellis.
* | 1350479_PIA11 Retaining screw scheduled to be delivered for 3/10/06 Screws will not have
phosphate coating. We may want to phos ourselves or apply a light oil.
* | 1353270_PIA04 Post left rod. New sections have been made but still need to be validated
scheduled to be completed on 3/7/06
* | 1353270_PIA21 Shaft. Die needs locating devices incorporated in it.
10 | Next Meeting scheduled for 3/8/06 @ 4:00pm in the corporate boardroom

## 3-23-06
U222 2nd / 3rd Row APQP
Meeting Minutes |  | 2006-03-23
Attendees: Lisa Bilbrey / Steve Markoc / Scott Barko / Greg Peltier / Dave Zultec /
Paul Drouillard / Phil Bryan / Kyle Lussier / Dick St.Pierre / Tom Brockman / Todd Van Hal
* | April 3rd 2006 JVD Manufacturing will be available
* | We need to look at a different screw gun or possibly a plastics change ( Phil B )
* | 3rd row locking features are not robust enough on the bottom of the shell. Flight molds has
made proposals to correct these issues. They owe quotes with cost and timing to JCI
* | 3rd row efforts bracket can be bent when putting the pawl nut on. When they are bent they interfere
with the plastics.
* | 30 - 40pcs. Out of 400pcs built on 2nd row exhibited chuck.
* | 2nd row has a stack up issue that shows that the parts may have chuck or possibly not lock.
* | Some screw heads snapped of during the build due to over torquing. A cordless drill was used during the
build not a torque gun. This may not be an issue if a torque gun is used.
* | What is the lead times for all components (Kyle)
* | We need direction from the customer on what coating we are to use for the posts.
* | Mark B to perform mini sled on 2nd / 3rd row parts with powder coated legs.
* | We need to generate a list of what components are above a rockwell of 39C
* | Panasonic welder will be delivered on 4/5/06
* | Next build of parts the welded skeletons will be done at Pioneer
* | We need to look at the 3rd row inertia lock spring, it needs some type of retention feature.
* | List of what equipement and resources will be needed at JVD Manufacturing.
* | Andy Pinard to make a packaging proposal
* | Scott to talk to JCI about possibly splitting the cost of returnable containers the thought is that we could ship to
Saltillo - Saltillo could use the same container to ship BWI in Warren - Empties could be sent to WMPI
* | Need to follow up with MIT about proposals to protect the strap from dirt and grease.
* | JCI had us add SC / CC's to the drawing. Mark L. has updated the drawings we need to have a meeting to
review the additions and determine what cost impact they have before the drawings get released.

## 3-25-06
U222 2nd / 3rd Row APQP
Meeting Minutes |  | 2006-03-25
Attendees: Lisa Bilbrey / Steve Markoc / Scott Barko / Greg Peltier / Dave Zultec / Lionel Peltier
Paul Drouillard / Phil Bryan / Kyle Lussier / Dick St.Pierre / Tom Brockman / Todd Van Hal
* | WMG needs a document from JCI stating that we can proceed with the current components
that are above 39HRC
* | Blanks from post are to be cut out of pre-drawn material. Jim V. to aquire the material.
* | April 3rd the assembly equipment will be moved into JVD
* | April 10th the robotic line will be moved into JVD
* | Prototype components required for latest P.O. received can be delivered from suppliers within 2 weeks
from receipt of P.O.'s
* | Steve M. to follow up on deliverables from PPAP'd suppliers.
* | Kyle L. / Mark C / to get with Tom B. / Paul D. about what tools and equipment will be required to build at JVD
* | Dave Z. to provide a cost sheet for team to review.
* | Todd to create a change notebook so that we can keep track of all changes and ensure that the appropriate
costs are captured.
* | 3rd row efforts bracket can get bent when pushing the pawl nut on Tom B. and kyle to address.
* | We are to proceed with the mechanical plating on the posts. The customer is calling the recent issue a
quality issue and not a design issue.
* | We need to determine what the process will be for the projection welding on the 3rd row lock lever and pin.
* | Taping of mechs. Needs to be quoted to JCI. JCI has not issue a PCR as of yet.
* | Mark L / Scott B / Phil F / Todd V H to have meeting on 3/29/06 to review the SC / CC's that JCI wants us to
add and determine what cost impact it has to us.
* | Scott / Todd to address latest P.O's received from JCI. JCI changed the purchase price to $80.00 with out
authorization from WMG
* | Quality Manager is needed at JVD to start preparing the Control Plans, FMEA's etc.

## 3-28-06
U222 2nd / 3rd Row APQP
Meeting Minutes |  | 2006-03-28
Attendees: Lisa Bilbrey / Steve Markoc / Scott Barko / Greg Peltier / Dave Zultec / Lionel Peltier
Paul Drouillard / Phil Bryan / Kyle Lussier / Dick St.Pierre / Tom Brockman / Todd Van Hal
* | WMG still needs a document from JCI stating that we can proceed with the current components
that are above 39HRC JCI has sent several requests to Ford
* | April 3rd assembly equipment will be moved into JVD.
* | Week of April 10th the robotic line is scheduled to be moved into JVD.
* | Dave Z provided a cost analysis sheet for 2nd and 3rd row for the team to review. Scott B. to work with
Dave to fill in any blank columns.
* | Next shipment of lock levers are to come in heat treated with no coating. 30pcs. To come in not heat treated
for testing purposes.
* | Lionel and Tom to look at projection welding process.
* | JCI purchasing is issuing PCR's to capture all items that have not been quoted to date. ( taping, sock )
* | Meeting was held to review the SC / CC's that JCI wants us to add to the drawings. A chart was created
that identifies the additions, and if they are captured in existing gauges. Todd to get clarification of what
JCI 's expectations are for SC / CC's
* | JCI Saltillo is requesting 2 individuals from WMG to go to Saltillo for next build. ( we are scheduled to ship parts
4/5/06 )
* | E-mail was sent to JCI requesting the prototype P.Q.'s be updated to $130.26 for 3rd row parts vs. the $80.00
that is currently on the P.Q.'s ( our component costs are $106.00 )
* | It was verbally communicated to JCI Supplier Quality that our new PPAP date will be 5/15/06. This will be followed
up in writing.
* | Lionel gave Phil permission to hire a Quality Manager for JVD.

## Sheet2
U222 APQP 2nd & 3rd row |  |  |  | Date: 4/20/06
Attendees: Scott B. / Phil F. / Paul D. / Jim V. / Todd VH / Kyle L. / Phil B. / Tom B. / Dick S. / Marc C / Greg P / Steve M /
Number | Issue | Responsible Persons | Open / Closed | Comments
1 | Post Legs. Availability / Quality / Production Tools | Tom B / Phil / Mike P / Mark L |  | Ellis to build tunnel gauge
2 | FEU Build Quantities / Build and Delivery Plan | Scott / Kyle / Todd / Jim
3 | Weld fixtures for 2nd & 3rd | Tom B / George H / Mike P
4 | Projection Welding | Paul / Glen / Phil B
5 | Lock Lever Rivet Machine 3rd row needs to be Designed & Built * | Paul D / Lionel
6 | 3rd row rivetor - Jim to provide list of issues to Paul / Tom | Jim / Paul / Tom
7 | Step 4 of 3rd row assembly process is very labour intensive | Jim / Kyle
8 | 2nd/3rd package. Fedex maximum size/weight | Todd / Jim
9 | 2nd row lock lever rivetor | Jim / Marc C
10 | 2nd row shaft diameter is currently undersize. New heading punch has been ordered, expected to be in on 4-20-06 | Mike Pe / Jim L / Mike V
11 | Spring Silencer - to be looked at in production process | Jim
12 | 2nd row rivet machine | Tom B / Todd
13 | Loading dump spring - Phil B to looked at Centroy for tool | Phil B / PMS
14 | Shells cracking | Phil B
15 | Screw guns - need 1 additional screw gun 1 arm 1 tool holder also need 1 tool holder for existing screw gun | Phil B
16 | Stickers - continous improvement | Jim / Phil B
17 | Tape | Jim / Phil B
18 | Supplier Releases | Jim / Kyle
19 | Supplier PPAPS | Phil F / Steve
20 | Side cover screws (shoulder screws) | Phil
21 | Proto type PO's (need corrected pricing) | Scott / Todd
22 | Quality Manager needed for JVD and St.Clair | Phil F
23 | WMG PPAP 5/15/06 | WMG
24 | Mixed parts at platers - PMS work on detection in process | Phil B / PMS
25 | Dunage Disposal - Scott to find out what Plastech quoted for packaging | Scott
26 | Inventory levels | Jim / Kyle
27 | Inertia Spring (new engineering level) | Steve / Mark L / Todd
28 | Covers on strap | Steve / Todd
29 | SC/CC's - Steve to send out drawings to suppliers | Steve