## 2R
U-222 Supplier Matrix | 2nd Row MECH
Latest PPAP
Part Number | Part Name | Supplier | Level of Print | PPAP Status | Rev of PPAP | Sub. Date | Comments
1350479_pia01.drw | POST-RIGHT SLAVE | JVD | 6 - 1.6 | Internal |  | 2006-05-11
1350479_pia03.drw | POST-LEFT LOCK | JVD | 7 - 1.7 | Internal |  | 2006-05-11
1350479_pia05.drw | COVER SHELL | Plastech | 3 - 1.4 |  |  |  | No print issued.
1350479_pia06.drw | COVER SHELL | Plastech | 2 - 1.4 |  |  |  | No print issued.
1350479_pia07.drw | RELEASE CABLE - 1T3 STONE | Pangeo | 3 - 1.4 | Approved | Level 2 - 1.3 | 2006-05-22
1350479_pia07-strap.drw | RELEASE STRAP | MIT | 2 - 1.2 | N/A | Level 2 - 1.2 | N/A | Part of 1350479-PIA07
1350479_pia09.drw | LOCK STAMPING | Pellus | 6 - 1.7 | Internal |  | 2006-05-11
1350479_pia10.drw | SLAVE MOVEABLE STAMPING | Pellus | 5 - 1.5 | Internal |  | 2006-05-11
1350479_pia11.drw | RETAINING SCREW | Precision | 3 - 1.2 | Interim | Level 3 - 1.2 | 2006-05-22 | IMDS needed.
1350479_pia12.drw | DUMP SPRING | Springs n Things | 3 - 1.3 | Interim | Level 1 - 1.1 | 2006-05-22 | IMDS needed.
1350479_pia13.drw | SHAFT | PPI | 5 - 1.5 | Interim | Level 1 - 1.5 | 2006-05-11
1350479_pia18-washer.drw | LEVER PIVOT PIN WASHER | Fabory | 1 - 1.0 | Approved | Level 1 - 1.2 | 2006-05-22
1350479_pia18.drw | LEVER PIVOT PIN | Chicago Rivet | 1 - 1.0 | Approved | Level 3 - 1.9 | 2006-05-22
1350479_pia19.drw | LEFT SIDE COVER PLATE | Hawk | 1 - 1.0 | Approved | Level 2 - 1.7 | 2006-05-22
1350479_pia20.drw | LOCK LEVER | GFM | 1 - 1.0 | Approved | Level 21 - 1.9 | 2006-05-22
1350479_pia21.drw | CATCH SPRING | Dominion | 1 - 1.0 | Approved | Level 11- 1.4 | 2006-05-22
1350479_pia22.drw | RETAINING SCREW | Systematic | 1 - 1.0 | Approved | Level 14 - 1.8 | 2006-05-22
1350479_pia23.drw | RIGHT SIDE COVER PLATE | Hawk | 1 - 1.0 | Approved | Level 4 - 1.8 | 2006-05-22
1350479_pia24.drw | BRONZE BUSHING | Easterm Sintered | 1 - 1.0 | Approved | Level Rel - 1.2 | 2006-05-22
1350479_pia25.drw | TUBE HEADREST FRAME | Pellus | 1 - 1.0 | Approved | Level 1 - 1.2 | 2006-05-22
1350479_pia26.drw | HEADREST BRACE | Ellis Mfg. | 1 - 1.0 | Approved | Level 3 - 1.3 | 2006-05-22
1350479_pia27.drw | ROTATIONAL STOP PIN | Chicago Rivet | 1 - 1.0 | Approved | Level 1 - 1.3 | 2006-05-22
1350479_pia28.drw | STOP BUMPER | LDB | 1 - 1.0 | Approved | Level 7 - 1.4 | 2006-05-22

## 3R
U-222 Supplier Matrix | 3rd Row MECH
Latest PPAP
Part Number | Part Name | Supplier | Level of Print | PPAP Status | Rev of PPAP | Sub. Date | Comments
1353270_pia02.drw | REAR SHELL | Plastech | 2 - 1.6 |  |  |  | No print issued.
1353270_pia03.drw | FRONT SHELL | Plastech | 2 - 1.5 |  |  |  | No print issued.
1353270_pia04.drw | POST- LEFT ROD | JVD | 7 - 1.7 | Internal |  | 2006-05-11
1353270_pia05.drw | POST- RIGHT ROD | JVD | 5 - 1.5 | Internal |  | 2006-05-11
1353270_pia06.drw | LOCK STAMPING | Pellus | 11 - 4.9 | Internal |  | 2006-05-11
1353270_pia07.drw | SLAVE STAMPING | Pellus | 5 - 1.4 | Internal |  | 2006-05-11
1353270_pia09.drw | LOCK LEVER | GFM | 6 - 1.6 | Approved | Level 4 | 2006-05-22
1353270_pia09-asm.drw | LOCK LEVER - PIN ASSEMBLY | JVD | 1 - 1.1 | Internal |  | 2006-05-11
1353270_pia10.drw | TUBE HEADREST FRAME | JVD | 1 - 1.1 | Internal |  | 2006-05-11
1353270_pia11.drw | HEADREST BRACE | Ellis Mfg | 1 - 1.4 | Approved | Level 1 - 1.4 | N/A
1353270_pia12.drw | DUMP SPRING | Dominion | 2 - 1.4 | Approved | Level 1 - 1.3 | 2006-05-22
1353270_pia15.drw | CATCH SPRING | Springs n Things | 6 - 1.8 | Interim | Level 6 - 1.8 | 2006-05-22 | IMDS needed.
1353270_pia16.drw | CABLE ANCHOR | Peerless | 2 - 1.2 | Approved | Level Rel - 2.7 | 2006-05-22
1353270_pia17.drw | PIN - PAWL RELEASE | Formnet | 4 - 1.4 | Approved | Level 4 - 1.4 | 2006-05-22
1353270_pia18.drw | RELEASE CABLE | Pangeo | 7 - 1.6 | Approved | Level 4 - 1.2 | 2006-05-22
1353270_pia21.drw | SHAFT | JVD | 5 - 1.4 | Internal |  | 2006-05-11
1353270_pia21-head.drw | SHAFT | Formnet | 2 - 1.2 | Approved | Level Rel - 1.0 | 2006-05-22
1353270_pia24.drw | RETAINING SCREW | Precision | 3 - 1.3 | Interim | Level 2 - 1.2 | 2006-05-22 | IMDS needed.
1353270_pia31.drw | ISOLATOR | Brahm | 3 -1.6 | Approved | Level 1 - 1.4 | 2006-05-22
1353270_pia32.drw | BRONZE BUSHING | Eastern Sintered | 2 - 1.3 | Approved | Level 2 - 1.3 | 2006-05-22
1353270_pia35.drw | LEVER PIVOT PIN | Chicago Rivet | 4 - 1.6 | Approved | Level 2 - 1.4 | 2006-05-22
1353270_pia36.drw | EXTENSION SPRING | Springs n Things | 4 - 1.7 |  |  | 2006-05-22
1353270_pia39.drw | MANUAL RELEASE STRAP | M.I.T. | 1 - 1.4 |  |  | 2006-05-22
1353270_pia40.drw | EFFORT BRKT | Peerless | 2 - 1.5 |  |  | 2006-05-22
1353270_pia40-asm.drw | PIN - STAMPING ASM | Peerless | 1 - 1.0 |  |  | 2006-05-05
1353270_pia41.drw | PIN - PAWL RELEASE | Chicago Rivet | 2 - 1.6 | Approved | Level 1 - 1.3 | 2006-05-22
1353270_pia42.drw | LEVER | Ellis Mfg | 2 - 1.4 | Approved | Level 1 - 1.3 | N/A
1353270_pia43.drw | ISOLATER | National Molding | 5 - 1.5 | Approved | Level 4 - 1.3 | 2006-05-22
1353270_pia44.drw | INERTIA LOCK | Canada Stamping | 3 - 1.8 | Approved | Level 2 - 1.6 | 2006-05-22
l0020752_pia05.drw | PAWL NUT | Fabory | Rel - 1.0 | Approved | Level Rel - 1.0 | N/A
l0023286_pia04_washer.drw | LEVER PIVOT PIN WASHER | Fabory | 1 - 1.2 | Approved | Level 1 - 1.2 | N/A