## 2nd Row
JVD MANUFACTURING LTD
U222 - 2nd ROW INVENTORY LAUNCH PLAN
2006-05-02
Due to the lack of schedules JVD has had to make assumptions on what component quantities we will require in preparation for program
launch. As a result, we have had to make inventory level assumptions for June and July. For June 1 our desired inventory level for each component is 1 week
(12,500 pcs) at full production requirements and for July 3 our desired inventory level for each component is 4 week (50,000 pcs) at full production requirements.
In order to achieve our desired inventory levels and meet our supplier lead time requirements JVD has been issues releases to our suppliers since early March.
Formula for Calculating Desired Inventory Levels
- JCI yearly projection for 3rd row parts - 500,000 pcs
- number of weeks in a year - 48
- extra capacity factor - 15 %
- scrap factor - 5 %
- therefore, 500,000 pcs / 48 = 10,416 pcs x 20 % (15 % + 5 %) = 12,499 pcs per week
DELIVERY
|  |  |  | LEAD TIME | ACTUAL | DESIRED | DESIRED
PART | PART | SUPPLIER | Usage Per | IN WEEKS | INVENTORY | INVENTORY | INVENTORY
NUMBER | DESCRIPTION | NAME | Assembly | (including transit) | AS OF 5/4/06 | ON 6/1/06 | ON 7/3/06
1350479_pia01.drw | POST-RIGHT SLAVE | JVD | 1 | internal | 33 | 12500 | 50000
1350479_pia03.drw | POST-LEFT LOCK | JVD | 1 | internal | 28 | 12500 | 50000
1350479_pia05.drw | COVER SHELL | Plastech | 1 | ? | 51 | 12500 | 50000
1350479_pia06.drw | COVER SHELL | Plastech | 1 | ? | 72 | 12500 | 50000
1350479_pia07.drw | RELEASE CABLE | Pangeo | 1 | 10 | 5B8-700, 4T1-451 | 12500 | 50000
1350479_pia07-strap.drw | RELEASE STRAP | MIT |  | part of P/N 1350479-PIA07 | 1T3-361, 6T7-274 | n/a | n/a
1350479_pia09.drw | LOCK STAMPING | Canada Stampings | 1 | 4 | 1692 | 12500 | 50000
1350479_pia10.drw | SLAVE MOVEABLE STAMPING | Canada Stampings | 1 | 4 | 1963 | 12500 | 50000
1350479_pia11.drw | RETAINING SCREW | Precision | 2 | 4 | 1793 | 25000 | 100000
1350479_pia12.drw | DUMP SPRING | Springs n Things | 1 | 4 | 7200 | 12500 | 50000
1350479_pia13.drw | SHAFT | PPI | 1 | 2 | 993 | 12500 | 50000
1350479_pia18-washer.drw | LEVER PIVOT PIN WASHER | Fabroy | 1 | 6 | 1000 | 12500 | 50000
1350479_pia18.drw | LEVER PIVOT PIN | Chicago Rivet | 1 | 6 | 480 | 12500 | 50000
1350479_pia19.drw | LEFT SIDE COVER PLATE | Hawk | 1 | 4 | 2238 | 12500 | 50000
1350479_pia20.drw | LOCK LEVER | GFM | 1 | 4 | 950 | 12500 | 50000
1350479_pia21.drw | CATCH SPRING | Dominion | 1 | 4 | 1408 | 12500 | 50000
1350479_pia22.drw | RETAINING SCREW | Systematic | 2 | 6 | 2492 | 25000 | 100000
1350479_pia23.drw | RIGHT SIDE COVER PLATE | Hawk | 1 | 4 | 753 | 12500 | 50000
1350479_pia24.drw | BRONZE BUSHING | Eastern Sintered | 2 | 4 | 9500 | 25000 | 100000
1350479_pia25.drw | TUBE HEADREST FRAME | JVD | 1 | internal | 997 | 12500 | 50000
1350479_pia26.drw | HEADREST BRACE | Ellis Mfg | 1 | 1 | 6000 | 12500 | 50000
1350479_pia27.drw | ROTATIONAL STOP PIN | Chicago Rivet |  | part of P/N 1350479-PIA28 | SEE BELOW | n/a | n/a
1350479_pia28.drw | STOP BUMPER | LDB | 1 | 6 | 1796 | 12500 | 50000
1350479_pia29 | SOCK | MIT | 1 | 6 | 362 | 12500 | 50000

## 3rd Row
JVD MANUFACTURING LTD
U222 - 3rd ROW INVENTORY LAUNCH PLAN
2006-05-02
Due to the lack schedules JVD has had to make assumptions on what component quantities we will require in preparation for program
launch. As a result, we have had to make inventory level assumptions for June and July. For June 1 our desired inventory level for each component is 1 week
(12,500 pcs) at full production requirements and for July 3 our desired inventory level for each component is 4 week (50,000 pcs) at full production requirements.
In order to achieve our desired inventory levels and meet our supplier lead time requirements JVD has been issues releases to our suppliers since early March.
Formula for Calculating Desired Inventory Levels
- JCI yearly projection for 3rd row parts - 500,000 pcs
- number of weeks in a year - 48
- extra capacity factor - 15 %
- scrap factor - 5 %
- therefore, 500,000 pcs / 48 = 10,416 pcs x 20 % (15 % + 5 %) = 12,499 pcs per week
DELIVERY
|  |  |  | LEAD TIME | ACTUAL | DESIRED | DESIRED
PART | PART | SUPPLIER | Usage Per | IN WEEKS | INVENTORY | INVENTORY | INVENTORY
NUMBER | DESCRIPTION | NAME | Assembly | (including transit) | AS OF 5/4/06 | ON 6/1/06 | ON 7/3/06
1353270_pia02.drw | REAR SHELL | Plastech | 1 | ? | 0 | 12500 | 50000
1353270_pia03.drw | FRONT SHELL | Plastech | 1 | ? | 10 | 12500 | 50000
1353270_pia04.drw | POST- LEFT ROD | JVD | 1 | internal | 167 | 12500 | 50000
1353270_pia05.drw | POST- RIGHT ROD | JVD | 1 | internal | 230 | 12500 | 50000
1353270_pia06.drw | LOCK STAMPING | Canada Stampings | 1 | 4 | 3000 | 12500 | 50000
1353270_pia07.drw | SLAVE STAMPING | Canada Stampings | 1 | 4 | 3000 | 12500 | 50000
1353270_pia09.drw | LOCK LEVER | GFM | 1 | part of P/N 1353270-PIA09-asm | SEE BELOW | 12500 | 50000
1353270_pia09-asm.drw | LOCK LEVER - PIN ASSEMBLY | JVD | 1 | internal | 356 | 12500 | 50000
1353270_pia10.drw | TUBE HEADREST FRAME | JVD | 1 | internal | 609 | 12500 | 50000
1353270_pia11.drw | HEADREST BRACE | Ellis Mfg | 1 | 1 | 6000 | 12500 | 50000
1353270_pia12.drw | DUMP SPRING | Dominion | 1 | 4 | 3900 | 12500 | 50000
1353270_pia15.drw | CATCH SPRING | Springs n Things | 1 | 4 | 1287 | 12500 | 50000
1353270_pia16.drw | CABLE ANCHOR | Peerless | 1 | 4 | 9000 | 12500 | 50000
1353270_pia17.drw | PIN - PAWL RELEASE | Formnet | 1 | 6 | 2500 | 12500 | 50000
1353270_pia18.drw | RELEASE CABLE | Pangeo | 1 | 14 | 1623 | 12500 | 50000
1353270_pia21.drw | SHAFT | JVD | 1 | part of P/N 1353270-PIA21head | 985 | 12500 | 50000
1353270_pia21-head.drw | SHAFT | Formnet | 1 | 6 | SEE ABOVE | 12500 | 50000
1353270_pia24.drw | RETAINING SCREW | Precision | 2 | 4 | 2445 | 25000 | 100000
1353270_pia31.drw | HYTREL ISOLATOR | Brahm | 2 | 4 | 4000 | 25000 | 100000
1353270_pia32.drw | BRONZE BUSHING | Eastern Sintered | 2 | 4 | 7448 | 25000 | 100000
1353270_pia35.drw | LEVER PIVOT PIN | Chicago Rivet | 1 | 6 | 221 | 12500 | 50000
1353270_pia36.drw | EXTENSION SPRING | Springs n Things | 1 | 4 | 1094 | 12500 | 50000
1353270_pia39.drw | MANUAL RELEASE STRAP | M.I.T. | 1 | 6 | 762 TOTAL | 12500 | 50000
1353270_pia40.drw | EFFORT BRKT | Peerless |  | part of P/N 1353270-PIA40-asm | 100 | n/a | n/a
1353270_pia40-asm.drw | PIN - STAMPING ASM | Peerless | 1 | 4 | 0 | 12500 | 50000
1353270_pia41.drw | PIN - PAWL RELEASE | Chicago Rivet |  | part of P/N 1353270-PIA40-asm | 2500 | n/a | n/a
1353270_pia42.drw | LEVER | Ellis Mfg | 1 | 1 | 178 | 12500 | 50000
1353270_pia43.drw | ISOLATER | National Molding | 1 | 6 | 300 | 12500 | 50000
1353270_pia44.drw | INERTIA LOCK | Canada Stamping | 1 | 6 | 30 | 12500 | 50000
l0020752_pia05.drw | PAWL NUT | Fabory | 3 | 6 | 2000 | 37500 | 150000
l0023286_pia04_washer.drw | LEVER PIVOT PIN WASHER | Fabory | 1 | 6 | 1000 | 12500 | 50000