## Sheet1
ADVANCED QUALITY PLANNING CHECKLIST
| ATTENDEES: |  | Lisa Bilbrey, Phil Bryan, |  |  | PART NUMBER: L0023286AJ-28, L0042999AH-28, L0023287AJ-25, L0043001AH-25
| Phil Fairley, Scott Barko, Steve Markoc, Lionel Peltier, |  |  |  |  | L0020720AE01, 1T3, 4T1, 5B8: L0020751AE01, 1T3, 4T1, 5B8, 6H5
| Lisa Legras, Marilyn Clark, Evan Kayahara |  |  |  |  | PPAP DATE / LEVEL : March 7, 2006
PRODUCTION START DATE: July 2005
| DATE: | 2006-02-15
VOLUME: 60/40: 600,000: Quad: 100,000: 3rd Row: 40,000
CUSTOMER: Lear
PLANT (S) RESPONSIBLE: Centroy
SALES REP: Scott Barko: Pgm Manager: Lisa Bilbrey
# | PART PRINT / MATH DATA |  |  | YES | NO | N/A | COMMENTS | DATE | RESP.
1 | Ellis Tool has received math data from customer |  |  | X
2 | Prints have been generated |  |  | X
3 | Prints have been controlled and distributed |  |  | X
4 | Manufacturing tolerances are feasible |  |  | X
5 | SC/CC requirements are applicable |  |  | X |  |  | See YCYS Matrix
6 | Engineering specifications are defined and understood. |  |  | X
i.e. material, weld, coating, torque etc.
7 | Potential for hydrogen embrittlement has been considered in design. | [5 empty] | Mechanical Plating
8 | Part/component designs are final |  |  | X
9 | Supplementary drawings are required |  |  | X
10 | Supplementary drawings are controlled and distributed |  |  | X
# | FIXTURES / GAUGING |  |  | YES | NO | N/A | COMMENTS | DATE | RESP.
11 | Fixture(s) Design is complete |  |  | X
12 | Multiple Fixtures are required |  |  | X
13 | Customer fixture(s) are required |  |  |  | X
14 | All fixture(s) designs have been reviewed/approved |  |  | X
15 | Customer has reviewed/approved fixture designs |  |  | X
16 | Fixture builds are complete |  |  | X
17 | Fixture(s) are certified / R&R complete |  |  | X
# | PPAP REQUIREMENTS |  |  | YES | NO | N/A | COMMENTS | DATE | RESP.
18 | Level 3 PPAP is required |  |  | X
19 | Customer has specific PPAP requirements |  |  |  | X
20 | Customer has provided supplier manual |  |  | X |  |  | Lear Website
21 | Part dimensionals are required How many? |  |  | X |  |  | 3 PIECE
22 | PPAP has been assigned |  |  | X
23 | Other PPAP open issues |  |  |  | X |  | Pending VAVE (Cost savings - removal of button).
# | TOOLING |  |  | YES | NO | N/A | COMMENTS | DATE | RESP.
24 | Tool designs are complete |  |  | X
25 | Manufacturing plant has reviewed designs |  |  | X
26 | Additional equipment is required |  |  | X |  |  | FOAM LINE - 3RD ROW
27 | Outsourced tooling / equipment is required |  |  |  | X
28 | Tooling is complete |  |  | X
29 | Tooling has been developed |  |  | X
30 | Manufacturing plant has reviewed and approved tooling |  |  | X
2 of 3
# | SUB-COMPONENT REQUIREMENTS |  |  | YES | NO | N/A | COMMENTS | DATE | RESP.
31 | Outsourced components are required |  |  | X
32 | Supplier (s) have been reviewed |  |  | X
33 | Purchase orders have been issued |  |  | X
34 | Supplier evaluation/development is complete |  |  | X
35 | Supplier(s) have submitted PPAP and samples |  |  | X |  |  | ALL SUPPLIER PPAP'S HAVE BEEN RECEIVED AND APPROVED.
OTHER OPEN ISSUES OR CONCERNS
REFER TO APQP FOR ADDITIONAL INFORMATION .
DOC'S UPLOADED ON PROFILES (LEAR WEBSITE).
60/40 & Quad: Mechanical Plating (was electro-plating) and removal of button.
ECN # for Plating: E E013414
ECN # for Removal of Button: E E013301
3rd Row: Removal of button.
ECN # for Removal of Button: X 0089829
| FOQA18B | REL |  |  |  |  | 3 of 3